## Sheet1
Expense Tracker
OverVirew
|  |  |  | Project Part | Description
| Group Members |  |  | Project Idea | Create a Python Expense Tracker application
|  |  |  | Main Goal | Help users track and manage their expenses
| Member Name | Role |  | Interface | Mobile-friendly GUI application
| Najm Yaslam | Searching and getting Data |  | Features | Add expense, view expenses, simple reports
| Ibrahim Aldolaaee | Programming |  | Data Storage | Save expense data for later use
| Khalid Alghanemi | Testing |  | Future Features | Categories, charts, cloud sync
| Ahmed Alhashedi | Maintenance |  | Team Work | Planning, coding, testing, improvement
Project Progress
Weeks | Missons |  | deadline
Week 1 | Setting the project and giving the roles |  | 21/02/26 - 28/02/26
Week 2 | Searching for materials |  | 28/02/26 - 07/03/26
Week 3 | Getting the Data we need for the project |  | 07/03/26 - 14/03/26
Week 4 | Starting the programming by building the basics for the project |  | 14/03/26 - 21/03/26
Week 5 | Programming |  | 21/03/26 - 28/03/26
Week 6 | Design the GUI |  | 1/4/26 - 14/4/26
Week 7 | Creating the database |  | 15/4/26 - 28/4/26
Week 8 | Testing the App |  | 29/4/26 - 2/5/26
Week 9 | Getting the feedback and add the add-on |  | 3/5/26 - 23/5/26
The Budget
0 TL :)